## Completed_Links
Module | Type | Item | Link | Status | Evidence File | Last Updated (file mtime) | Confidence
Reels Feed | Screen | Reels feed page | http://localhost:3000/ and http://localhost:3000/reels | Completed | src/pages/ReelsFeedPage.jsx | 2026-04-16 | High
Browse | Screen | Categories list | http://localhost:3000/categories | Completed | src/pages/CategoriesPage.jsx | 2026-03-30 | High
Browse | Screen | Subcategories page | http://localhost:3000/categories/:categoryId | Completed | src/pages/SubcategoriesPage.jsx | 2026-03-30 | High
Browse | Screen | Category products listing | http://localhost:3000/categories/:categoryId/products | Completed | src/pages/CategoryProductsPage.jsx | 2026-04-02 | High
Product | Screen | Product detail | http://localhost:3000/products/:id | Completed | src/pages/ProductDetailPage.jsx | 2026-03-20 | High
Auth | Screen | Login page | http://localhost:3000/login | Completed | src/pages/LoginPage.jsx | 2026-03-30 | High
Auth | Screen | Signup page | http://localhost:3000/signup | Completed | src/pages/SignupPage.jsx | 2026-03-30 | High
Auth | Screen | Verify email OTP page | http://localhost:3000/verify-email-otp | Completed | src/pages/VerifyEmailOtpPage.jsx | 2026-03-30 | High
Auth | Screen | OAuth success | http://localhost:3000/oauth-success | Completed | src/pages/OAuthSuccessPage.jsx | 2026-03-30 | High
Onboarding | Screen | Welcome page | http://localhost:3000/welcome | Completed | src/pages/WelcomePage.jsx | 2026-03-31 | High
Onboarding | Screen | Profile setup page | http://localhost:3000/profile-setup | Completed | src/pages/ProfileSetupPage.jsx | 2026-03-31 | High
Chat | Screen | Chat inbox | http://localhost:3000/chat | Completed | src/pages/ChatInboxPage.jsx | 2026-03-20 | High
Chat | Screen | Chat thread | http://localhost:3000/chat/:threadId | Completed | src/pages/ChatThreadPage.jsx | 2026-03-30 | High
Post Ad | Screen | Legacy post ad form | http://localhost:3000/post-ad | Completed | src/pages/PostAdPage.jsx | 2026-04-06 | High
Post Ad | Screen | Dynamic post ad form UI shell | http://localhost:3000/post-ad-dynamic | Partially Completed | src/pages/PostAdDynamicFormPage.jsx | 2026-03-30 | High
Dashboard | Screen | Dashboard overview | http://localhost:3000/dashboard | Completed | src/pages/dashboard/DashboardOverviewPage.jsx | 2026-03-30 | High
Dashboard | Screen | Dashboard listings | http://localhost:3000/dashboard/listings | Completed | src/pages/dashboard/DashboardListingsPage.jsx | 2026-04-02 | High
Dashboard | Screen | Dashboard orders | http://localhost:3000/dashboard/orders | Partially Completed | src/pages/dashboard/DashboardOrdersPage.jsx | 2026-03-30 | High
Dashboard | Screen | Dashboard wishlist | http://localhost:3000/dashboard/wishlist | Completed | src/pages/dashboard/DashboardWishlistPage.jsx | 2026-03-30 | High
Dashboard | Screen | Dashboard messages | http://localhost:3000/dashboard/messages | Completed | src/pages/dashboard/DashboardMessagesPage.jsx | 2026-03-30 | High
Dashboard | Screen | Dashboard notifications | http://localhost:3000/dashboard/notifications | Completed | src/pages/dashboard/DashboardNotificationsPage.jsx | 2026-03-30 | High
Dashboard | Screen | Dashboard settings | http://localhost:3000/dashboard/settings | Completed | src/pages/dashboard/DashboardSettingsPage.jsx | 2026-03-30 | High
Profile | Screen | Public user profile | http://localhost:3000/user/:id | Completed | src/pages/UserProfilePage.jsx | 2026-03-20 | High
Profile | Screen | Followers / following | http://localhost:3000/user/:id/:type | Completed | src/pages/FollowersFollowingPage.jsx | 2026-03-20 | High
Admin | Screen | Admin dashboard | http://localhost:3000/admin | Completed | src/pages/AdminDashboardPage.jsx | 2026-03-31 | High
Admin | Screen | Admin categories | http://localhost:3000/admin/categories | Completed | src/pages/AdminCategoriesPage.jsx | 2026-03-30 | High
Admin | Screen | Admin filters | http://localhost:3000/admin/filters | Completed | src/pages/AdminFiltersPage.jsx | 2026-03-30 | High
Admin | Screen | Admin dealers | http://localhost:3000/admin/dealers | Completed | src/pages/AdminDealersPage.jsx | 2026-03-20 | High
Admin | Screen | Admin roles | http://localhost:3000/admin/roles | Completed | src/pages/AdminRolesPage.jsx | 2026-03-20 | High
Admin | Screen | Role permissions | http://localhost:3000/admin/roles/:id/permissions | Completed | src/pages/AdminRolePermissionsPage.jsx | 2026-03-20 | High
API | Endpoint Set | Documented API surface | http://localhost:5002/api-docs and /api-docs.json | Completed | API_LIST.md | 2026-04-03 | High

## Pending_Pages_Design_Dev
Module | Pending Page/Screen | Design Pending | Development Pending | Evidence File | Action Items | Planned Start | Planned End | Effort | Status
Post Ad | Dynamic Post Ad submit flow | Design polish required for submit/error/success states | Backend integration pending (TODO in code) | src/pages/PostAdDynamicFormPage.jsx | Create listing API wiring + validation + success UX | 2026-05-12 | 2026-05-15 | 4d | Planned
Post Ad | Server-driven dynamic form config | Design for loading/error/fallback states | Endpoint missing on backend | src/services/postAdFormConfigService.js | Add /api/post-ad-form-config + admin config controls | 2026-05-16 | 2026-05-20 | 5d | Planned
Checkout/Orders | Checkout page + payment flow | Complete checkout UX screens | Order creation flow missing; orders page indicates empty until checkout | src/pages/dashboard/DashboardOrdersPage.jsx | Add checkout APIs + order placement + order lifecycle | 2026-05-21 | 2026-05-30 | 10d | Planned
Chat | Price suggestion UI in chat | Finalize negotiation widget design | State exists but feature flow incomplete | src/pages/ChatThreadPage.jsx | Implement suggestion logic end-to-end or remove dead code | 2026-05-31 | 2026-06-02 | 3d | Planned
Admin | Category-filter assignment page route | Review page UX and navigation hierarchy | Page exists but not wired in routing | src/pages/AdminCategoryFiltersPage.jsx | Route wiring + permissions + QA | 2026-06-03 | 2026-06-04 | 2d | Planned
Search | Popular search from analytics/API | Design dropdown behavior for dynamic data | Hardcoded popular searches | src/components/Search/SearchBar.jsx | API integration + ranking logic | 2026-06-05 | 2026-06-06 | 2d | Planned
Home | HomePage route decision | Decide if Home design should be used | Page present but not used in app routing | src/pages/HomePage.jsx | Wire route or deprecate page | 2026-06-07 | 2026-06-07 | 1d | Planned
Dashboard | Legacy UserDashboardPage route decision | Confirm if this design should be retained | Page present but not routed | src/pages/UserDashboardPage.jsx | Wire or archive to reduce maintenance | 2026-06-08 | 2026-06-08 | 1d | Planned

## Old_Modules_Updates
Module | Current Maturity | What is Done | Design Update Pending | Development Update Pending | Planned Start | Planned End | Risk
Auth | Stable | Login/signup/OTP/OAuth screens and APIs implemented | Polish validation and edge-case UX | Regression + security test pass | 2026-05-12 | 2026-05-14 | Low
Browse & Categories | Stable | Categories/subcategories/products discovery implemented | Improve empty and loading design consistency | Facets/filter QA and performance pass | 2026-05-15 | 2026-05-18 | Low
Product Detail | Stable | Detail page and related products implemented | Micro-interaction and media fallback polish | SEO/share metadata + analytics events | 2026-05-19 | 2026-05-21 | Low
User Dashboard | Mostly Stable | Dashboard sections available | Unify card/table patterns across tabs | Orders flow depends on checkout module | 2026-05-22 | 2026-05-27 | Medium
Admin Core | Stable | Admin categories/filters/dealers/roles available | Improve IA for module navigation | Expose category-filter mapping route and QA | 2026-05-28 | 2026-05-31 | Medium

## New_Modules_Timeline
New Module | Type | Priority | Scope | Planned Start | Planned End | Duration | Dependency
Dynamic Post Ad (schema driven) | New | High | Frontend submit + backend schema endpoint + admin configurability | 2026-06-01 | 2026-06-10 | 10d | Depends on products API contract
Checkout + Order Creation | New | High | Checkout UI, payments stub/integration, order creation, status tracking | 2026-06-11 | 2026-06-24 | 14d | Cross-team: backend + payment gateway decisions
Chat Negotiation Helper | New | Medium | Price suggestion UX and service logic completion | 2026-06-25 | 2026-06-29 | 5d | Can be descoped if not priority
Search Intelligence | New | Medium | Popular searches from analytics + ranking endpoint | 2026-06-30 | 2026-07-03 | 4d | Needs event tracking data source

## Pending_Consolidated
Category | Item | Owner | Target End | Remarks
Development | Dynamic Post Ad submit flow | Post Ad | 2026-05-15 | Create listing API wiring + validation + success UX
Development | Server-driven dynamic form config | Post Ad | 2026-05-20 | Add /api/post-ad-form-config + admin config controls
Development | Checkout page + payment flow | Checkout/Orders | 2026-05-30 | Add checkout APIs + order placement + order lifecycle
Development | Price suggestion UI in chat | Chat | 2026-06-02 | Implement suggestion logic end-to-end or remove dead code
Development | Category-filter assignment page route | Admin | 2026-06-04 | Route wiring + permissions + QA
Development | Popular search from analytics/API | Search | 2026-06-06 | API integration + ranking logic
Development | HomePage route decision | Home | 2026-06-07 | Wire route or deprecate page
Development | Legacy UserDashboardPage route decision | Dashboard | 2026-06-08 | Wire or archive to reduce maintenance
Design | Dynamic Post Ad submit flow | Post Ad | 2026-05-15 | Design polish required for submit/error/success states
Design | Server-driven dynamic form config | Post Ad | 2026-05-20 | Design for loading/error/fallback states
Design | Checkout page + payment flow | Checkout/Orders | 2026-05-30 | Complete checkout UX screens
Design | Price suggestion UI in chat | Chat | 2026-06-02 | Finalize negotiation widget design
Design | Category-filter assignment page route | Admin | 2026-06-04 | Review page UX and navigation hierarchy
Design | Popular search from analytics/API | Search | 2026-06-06 | Design dropdown behavior for dynamic data
Design | HomePage route decision | Home | 2026-06-07 | Decide if Home design should be used
Design | Legacy UserDashboardPage route decision | Dashboard | 2026-06-08 | Confirm if this design should be retained